## Feature Overview
UNO ERP - FEATURE SPECIFICATION & TECHNICAL BREAKDOWN
FEAT-HOTEL-AI-01: RateHawk Real-Time Hotel Availability & AI Multi-Tier Package Generator (3★ vs 4★)
Epic / Domain: | Hotel Sourcing, Tour Quotation & AI Automation |  | Target Sprints: | Sprint 6.1 (Backend/API) & Sprint 6.2 (Frontend/UI/E2E)
Feature Key: | FEAT-HOTEL-AI-01 |  | Total Story Points: | 21 Points (~64 Engineering Hours)
Business Analyst: | BusinessAnalyst (ScrumTeamSimulator) |  | Tech Lead / Architect: | TechLead (ScrumTeamSimulator)
Lead Developers: | FSDeveloper (Backend), FrontendLeadDeveloper (UI) |  | QA / Automation: | Test_Automation_Engineer (Playwright E2E)
Commercial Model: | RateHawk B2B API ($0/mo fixed SaaS fee, Net Wholesale) |  | Status: | Ready for Sprint Backlog (DoR Approved)
EXECUTIVE BUSINESS PROBLEM & TECHNICAL SOLUTION SUMMARY
1. BUSINESS PROBLEM: DMC quoting operators spend 3-4 hours per inquiry manually searching hotel websites, calling suppliers, and calculating multi-city group package pricing. When agency clients request alternative 3★ vs. 4★ hotel comparisons, turnaround delays cause lost deals to faster competitors. 2. THE SOLUTION (FEAT-HOTEL-AI-01): Integrates RateHawk's WorldOTA REST API (ETG v3) to query live wholesale hotel rates for 3★ and 4★ properties in parallel (<600ms). An AI synthesis engine blends live hotel rates with Uno_ERP's contracted ground services (coaches, guides, excursions, taxes) to generate two complete, costed tour packages (Option A: 3★ Economy vs. Option B: 4★ Standard) in under 4 seconds. 3. END-TO-END OPERATIONAL & ACCOUNTING IMPACT: - 1-Click Itinerary Ingestion: Selected package creates native Tour and TourService records without manual typing. - Accounts Payable (AP) Automation: Confirmed reservations auto-accrue supplier invoices in Uno_ERP's finance ledger. - Cancellation Penalty Safeguard: RateHawk penalty milestones populate TourCheckpointWidget to prevent financial loss. - Zero Fixed Platform Fee: Leverages RateHawk's $0/month model, avoiding expensive $650/mo middleware costs (ZentrumHub).
RESOURCE ALLOCATION & ROLE ASSIGNMENTS
Assigned Role | Agent / Team Member | Primary Responsibilities | Stories Owned | Est. Hours | Sprint Target
FSDeveloper | Full Stack Developer | Backend RateHawk API Gateway, Polly resilience, AI synthesis service, AP ledger accruals | STORY-01, STORY-02, STORY-05 | 28 hrs | Sprint 6.1
FrontendLeadDeveloper | Frontend Lead Developer | Live search modal, 3★ vs 4★ comparison cards, AI package comparison & 1-click apply | STORY-03, STORY-04 | 22 hrs | Sprint 6.2
FrontendDesigner | Frontend Designer | High-density UI wireframes, card contrast, mobile-responsive layouts, rating chips | STORY-03 (Design) | 4 hrs | Sprint 6.1
Test_Automation_Engineer | QA / E2E Manager | Playwright automated test suite in tests/e2e/, mock fixtures, financial invariant assertions | STORY-06 | 10 hrs | Sprint 6.2
TechLead | Solution Architect | Architecture governance, DTO boundary rules, rate staleness guardrails, code review | Governance | 4 hrs | Sprint 6.1-6.2
BusinessAnalyst | Requirements Lead | Story deconstruction, Acceptance Criteria [AC-XX], Definition of Ready gatekeeping | Backlog Owner | 4 hrs | Pre-Sprint

## User Stories & AC
FEAT-HOTEL-AI-01: USER STORIES & VERIFIABLE GHERKIN ACCEPTANCE CRITERIA [AC-XX]
Story ID | Title | Persona / Role | User Story Description | Acceptance Criteria (Gherkin Format) | Points | Priority | Assignee
STORY-01 | Backend RateHawk API Gateway & Multi-Star Availability Search | FSDeveloper | As a Tour Operator, I want to query live hotel rates in parallel across 3★ and 4★ categories for tour destinations, So that I get accurate, bookable room prices and cancellation terms in sub-seconds. | [AC-01-01]: Given destination cities (e.g. Budapest, Vienna, Prague), dates, and room breakdown (e.g. 15 Dbl, 3 Sgl), When calling POST /api/hotels/search-live, Then system queries RateHawk v3 in parallel and returns 3★ and 4★ available hotels in <600ms. [AC-01-02]: Given rate options returned, When hotel has free cancellation, Then system exposes exact FreeCancellationBefore timestamp. [AC-01-03]: Given a non-refundable room rate, When returned, Then system flags rate with isNonRefundable=true and amber warning chip. [AC-01-04] (Error Path): Given RateHawk API timeout or network failure, When search fails, Then system gracefully returns cached master-data hotels with fallback warning. | 5 | P0 | FSDeveloper
STORY-02 | AI-Empowered Multi-Tier Itinerary Package Generator Service | FSDeveloper | As a Quoting Specialist, I want the AI engine to generate 3★ Economy and 4★ Standard package alternatives simultaneously, So that I can present two balanced tour options to agency clients without manual calculation. | [AC-02-01]: Given live RateHawk hotel rates and contracted ground services (coaches, guides, excursions), When operator requests AI generation, Then backend invokes LLM with strict JSON schema to assemble two complete tour packages in <4 seconds. [AC-02-02]: Given Option A (3★) and Option B (4★), When generated, Then each variant contains day-by-day schedules, hotel allocations, and per-pax pricing calculated by the financial pivot engine. [AC-02-03]: Given target profit margin (e.g. 18%), When packages are built, Then selling prices automatically calculate to meet target margin. [AC-02-04] (Validation): Given malformed LLM response, When schema validation fails, Then system falls back to deterministic rule-based package generator. | 5 | P0 | FSDeveloper
STORY-03 | Frontend Live Hotel Search & 3★ vs 4★ Comparison UI Modal | FrontendLeadDeveloper | As an Operator, I want an interactive modal to inspect live hotel rates side-by-side with 3★ vs 4★ tabs, So that I can quickly select the optimal hotel for each stay. | [AC-03-01]: Given Tour Detail page, When operator clicks 'Search Live Hotels', Then modal opens pre-filled with tour dates, destinations, and room allocations. [AC-03-02]: Given search results, When viewing destination tab, Then hotels are grouped side-by-side by 3★ and 4★ tiers with meal plan, room type, and price per night. [AC-03-03]: Given hotel selection, When operator clicks 'Select Hotel', Then hotel rate is staged for active tour stay with rate lock countdown indicator. [AC-03-04]: Given high-density UI constraints, When rendering comparison cards, Then each card height is <=110px with badge chips for amenities and cancellation. | 3 | P0 | FrontendLeadDeveloper
STORY-04 | Frontend AI Package Comparison & 1-Click Itinerary Ingestion | FrontendLeadDeveloper | As an Operator, I want to preview the AI-generated 3★ vs 4★ tour packages side-by-side and commit with 1-click, So that active tour services and financials are instantly populated. | [AC-04-01]: Given generated packages, When comparison modal opens, Then Option A (3★ Economy) and Option B (4★ Standard) display side-by-side with total cost, revenue, and margin %. [AC-04-02]: Given package preview, When operator toggles itinerary details, Then day-by-day breakdown shows hotel name, city, coach transfers, and excursions. [AC-04-03]: Given operator clicks 'Apply Option B (4★) to Tour', When confirmed, Then TourService records are created in DB, rooming counts updated, and financial pivot refreshes in <1s. [AC-04-04]: Given applied package, When navigating to Tour Header, Then base fee, cost/pax, revenue/pax, and profit chips update with zero page reload. | 3 | P1 | FrontendLeadDeveloper
STORY-05 | Automated AP Invoice Accrual & Cancellation Checkpoint Guard | FSDeveloper | As a Financial Controller & Operations Manager, I want booked hotel stays to auto-create Accounts Payable accruals and register cancellation deadlines in the Checkpoint Gate, So that manual bookkeeping is eliminated and penalty deadlines are never missed. | [AC-05-01]: Given a tour advancing from Quote to Confirmed status, When RateHawk booking executes, Then system captures Order ID, Voucher URL, and Net Payable Cost into TourService. [AC-05-02]: Given confirmed booking, When checking /finance AP ledger, Then an AP invoice accrual exists with supplier 'RateHawk', exact net amount, and due date matching cancellation milestone. [AC-05-03]: Given cancellation penalty timestamp, When current date approaches within warning threshold (e.g. 5 days), Then TourCheckpointWidget renders amber warning 'Hotel Cancellation Penalty Imminent'. [AC-05-04] (Cancellation Flow): Given a cancelled tour, When status transitions to Cancelled before deadline, Then system calls RateHawk cancel API and voids AP accrual. | 3 | P1 | FSDeveloper
STORY-06 | Automated E2E Test Suite for Live Hotel Sourcing & Package Generation | Test_Automation_Engineer | As the QA & Test Automation Manager, I want Playwright automated test coverage for the live search and AI package workflows, So that regressions in rate calculation and financial pivot integrity are caught automatically. | [AC-06-01]: Given test script tests/e2e/test_ratehawk_hotel_sourcing.py, When executed, Then it validates search modal launch, city tab switching, 3★/4★ side-by-side rendering, and pre-book rate validation. [AC-06-02]: Given AI package generation test, When triggered, Then it verifies both 3★ and 4★ variants produce valid TourService records and financial pivot grand totals match. [AC-06-03]: Given tour status transition test, When advancing to Confirmed, Then test asserts AP accrual record creation and cancellation deadline badge in TourCheckpointWidget. | 2 | P1 | Test_Automation_Engineer

## Technical Subtasks
FEAT-HOTEL-AI-01: ENGINEERING SUBTASK WORK BREAKDOWN & ASSIGNMENTS
Subtask ID | Parent Story | Task Title | Architecture Layer | Assigned Developer | Est. Hours | Sprint | Technical Verification / Done Check
SUB-01-1 | STORY-01 | RateHawk Configuration & HttpClient Polly Registration | Backend / Core | FSDeveloper | 4 | Sprint 6.1 | RateHawkConfig registered in appsettings; typed client injected with 3 retries and circuit breaker
SUB-01-2 | STORY-01 | RateHawk Request/Response DTO Contracts & Mappings | Backend / DTOs | FSDeveloper | 4 | Sprint 6.1 | HotelSearchRequestDto, HotelRateOptionDto, RoomTypeRateDto authored with strict JSON serializers
SUB-01-3 | STORY-01 | Implement IRateHawkHotelService & ETG v3 Search Call | Backend / Services | FSDeveloper | 8 | Sprint 6.1 | Live search queries api.worldota.net/api/b2b/v3/hotel/search/ and parses multi-room responses
SUB-01-4 | STORY-01 | Parallel 3★ vs 4★ Multi-Star Search in HotelAvailabilityController | Backend / API | FSDeveloper | 6 | Sprint 6.1 | Task.WhenAll executes 3★ and 4★ search concurrently in <600ms total latency
SUB-01-5 | STORY-01 | Pre-Book Rate Check & Cancellation Timestamp Extraction | Backend / API | FSDeveloper | 4 | Sprint 6.1 | Calls /order/booking/form/ endpoint; extracts exact penalty date and verifies price stability
SUB-02-1 | STORY-02 | ItineraryOrchestrationService Master Data & Rate Aggregator | Backend / AI Service | FSDeveloper | 6 | Sprint 6.1 | Aggregates live hotel rates with DB contracted coach, guide, and excursion rates for tour dates
SUB-02-2 | STORY-02 | Author LLM Completion Prompt & Strict JSON Schema Parser | Backend / AI Service | FSDeveloper | 6 | Sprint 6.1 | Generates Option A (3★) and Option B (4★) with day-by-day services, meal plans, and margin %
SUB-02-3 | STORY-02 | Financial Pivot Mapping & Deterministic Fallback Engine | Backend / Financial | FSDeveloper | 4 | Sprint 6.1 | Computes per-pax Cost, Revenue, Net Margin; falls back to rule-based template if LLM fails
SUB-02-4 | STORY-02 | POST /api/tours/generate-multi-tier-packages Controller Endpoint | Backend / API | FSDeveloper | 4 | Sprint 6.1 | Swagger endpoint verified; returns clean PackageComparisonDto payload in <4s
SUB-03-1 | STORY-03 | UI/UX High-Density Component Wireframes & Rating Chips | UI/UX Design | FrontendDesigner | 4 | Sprint 6.1 | Figma/Tailwind layout mockups created complying with max-2-line header density rules
SUB-03-2 | STORY-03 | Create LiveHotelSearchModal.tsx with City Tabs & Star Filters | Frontend / Next.js | FrontendLeadDeveloper | 6 | Sprint 6.2 | Modal renders destination tabs (Budapest, Vienna, Prague) with room allocation pills
SUB-03-3 | STORY-03 | Side-by-Side 3★ vs 4★ Hotel Card Grid Component | Frontend / Next.js | FrontendLeadDeveloper | 6 | Sprint 6.2 | Compact cards (<=110px) render hotel photo, star rating, meal badge, and price/night
SUB-03-4 | STORY-03 | Frontend API Integration & Skeletons in TourDetailPage | Frontend / Next.js | FrontendLeadDeveloper | 4 | Sprint 6.2 | Wires searchLiveHotels() with shimmer skeletons, error alerts, and rate selection state
SUB-04-1 | STORY-04 | Create AIPackageComparisonModal.tsx Side-by-Side View | Frontend / Next.js | FrontendLeadDeveloper | 6 | Sprint 6.2 | Displays Option A vs Option B with visual margin progress meters and delta chips
SUB-04-2 | STORY-04 | 1-Click Apply Action & Optimistic TourService State Commit | Frontend / Next.js | FrontendLeadDeveloper | 4 | Sprint 6.2 | Replaces staged tour stays and ground services in state and commits to DB via API in <1s
SUB-04-3 | STORY-04 | Instant Top-Bar Financial Pivot & KPI Chip Synchronizer | Frontend / Next.js | FrontendLeadDeveloper | 4 | Sprint 6.2 | Refreshes Base Fee, Cost/Pax, Revenue/Pax, and Net Margin chips with zero page reload
SUB-05-1 | STORY-05 | EF Core Entity Schema Update for TourService Tracking | Database / EF Core | FSDeveloper | 3 | Sprint 6.1 | Adds ExternalBookingReference, CancellationDeadline, NetPayableCost to TourService model
SUB-05-2 | STORY-05 | EF Core Migration AddHotelBookingTracking & DB Update | Database / EF Core | FSDeveloper | 2 | Sprint 6.1 | Migration applied cleanly to SQL Server with 0 errors and backward-compatible nullable fields
SUB-05-3 | STORY-05 | Automated AP Ledger Accrual Generator on Tour Confirmation | Backend / Finance | FSDeveloper | 5 | Sprint 6.2 | Creates Accounts Payable invoice record with supplier 'RateHawk' and exact cancellation due date
SUB-05-4 | STORY-05 | TourCheckpointWidget Cancellation Milestone Watchdog | Frontend / Next.js | FSDeveloper | 4 | Sprint 6.2 | Warns operators when today is within 5 days of hotel cancellation penalty deadline
SUB-06-1 | STORY-06 | RateHawk Sandbox Mock Fixtures & Test Data Seeding | QA / Automation | Test_Automation_Engineer | 3 | Sprint 6.2 | Prepares deterministic JSON mocks for offline Playwright test runs
SUB-06-2 | STORY-06 | Playwright E2E Test: Live Hotel Search & Star Comparison | QA / Automation | Test_Automation_Engineer | 4 | Sprint 6.2 | Verifies modal open, city tab change, 3★ vs 4★ cards render, and hotel selection
SUB-06-3 | STORY-06 | Playwright E2E Test: AI Package Ingestion & AP Accrual Verification | QA / Automation | Test_Automation_Engineer | 3 | Sprint 6.2 | Asserts 1-click apply populates TourService and AP ledger record created in /finance

## API Contracts & Schema
TECHNICAL SPECIFICATION: API ENDPOINTS, DTOS & DATABASE SCHEMAS
1. NEW & EXTENDED REST API ENDPOINTS (Uno_API / Controllers / HotelAvailabilityController.cs)
HTTP Method | Route Path | Purpose | Request DTO | Response DTO | Latency SLA | Resilience Policy
POST | /api/hotels/search-live | Parallel 3★ vs 4★ hotel availability search | LiveHotelSearchRequestDto | LiveHotelSearchResponseDto | < 600ms | Polly: 3 retries (200ms backoff), circuit breaker 5 fails
POST | /api/hotels/rate-check | Pre-book price & cancellation penalty verification | HotelRateCheckRequestDto | HotelRateCheckResponseDto | < 400ms | Polly: 2 retries, fallback to last known valid rate
POST | /api/tours/generate-multi-tier-packages | AI Multi-Tier Package Generator (3★ vs 4★) | GenerateMultiTierRequestDto | MultiTierPackageResponseDto | < 4.0s | Timeout: 10s; Fallback: deterministic rule-based generator
POST | /api/tours/{id}/apply-package | Commit selected package into Tour & TourServices | ApplyTourPackageDto | TourDetailDto | < 800ms | Transaction Scope: Atomic DB rollback on failure
POST | /api/hotels/book-reservation | Finalize live booking with RateHawk | ExecuteBookingRequestDto | ExecuteBookingResponseDto | < 1.5s | Idempotency key header enforced; AP accrual auto-created
2. DATABASE ENTITY EXTENSION (Uno_API / Models / TourService.cs)
Field Name | Data Type | Nullability | Database Column | Default | Purpose & Business Rules
ExternalBookingRef | string? | NULL | NVARCHAR(100) | null | RateHawk Order / Partner ID for supplier reconciliation
VoucherUrl | string? | NULL | NVARCHAR(500) | null | Direct link to download official RateHawk hotel voucher PDF
CancellationDeadline | DateTime? | NULL | DATETIME2 | null | Timestamp when free cancellation ends; watched by TourCheckpointWidget
IsNonRefundable | bool | NOT NULL | BIT | 0 | Flags rate as strictly non-refundable upon reservation
NetPayableCost | decimal? | NULL | DECIMAL(18,2) | null | Raw wholesale net cost from RateHawk to reconcile against AP Invoice
MealPlanType | string? | NULL | NVARCHAR(50) | 'RO' | Room Only (RO), Bed & Breakfast (BB), Half Board (HB), Full Board (FB)

## RACI & Sprint Plan
SPRINT DELIVERY SCHEDULE & RACI GOVERNANCE MATRIX
1. SPRINT EXECUTION ROADMAP (Total: 2 Sprints / 10 Business Days)
Sprint Cycle | Primary Focus | Key Deliverables | Allocated Roles | Total Points | Exit Criteria
Sprint 6.1 (Days 1 - 5) | Backend Architecture, RateHawk API Adapter & Database Schema | • IRateHawkHotelService & Polly typed client • EF Core migration & schema update • Parallel 3★ vs 4★ search endpoint (<600ms) • ItineraryOrchestrationService with LLM prompt • UI Wireframes & Figma layout | FSDeveloper (Lead) TechLead (Architecture) FrontendDesigner (Wireframes) | 12 pts | • Zero compiler warnings • RateHawk sandbox certification test passes • Swagger endpoints verified with live test data
Sprint 6.2 (Days 6 - 10) | Frontend UI, Comparison Modals, AP Invoicing & Playwright E2E | • LiveHotelSearchModal.tsx with star comparison • AIPackageComparisonModal.tsx with 1-click apply • Auto-accrual of AP invoices in /finance • TourCheckpointWidget cancellation warning • Automated Playwright E2E test suite | FrontendLeadDeveloper (Lead) FSDeveloper (AP/Ledger) Test_Automation_Engineer (E2E) | 9 pts | • 1-Click apply populates TourServices in <1s • Financial chips refresh optimistically • All Playwright E2E tests pass in CI
2. RACI GOVERNANCE MATRIX (R = Responsible, A = Accountable, C = Consulted, I = Informed)
Project Deliverable / Component | ProductOwner | TechLead | BusinessAnalyst | FSDeveloper | FrontendLeadDev | QAManager / E2E
RateHawk Commercial Setup & Sandbox Key Provisioning | A | C | R | I | I | I
RateHawk Backend API Adapter & DTO Architecture | I | A | C | R | I | C
AI Multi-Tier Package Generator & Prompt Schema | C | A | C | R | C | I
Frontend 3★ vs 4★ Comparison Modal & 1-Click Apply | C | C | C | C | R / A | I
Database Migration & Accounts Payable (AP) Accruals | I | A | I | R | I | I
Checkpoint Gatekeeper & Cancellation Safeguards | I | C | C | R | R | C
Automated Playwright E2E Test Suite in tests/e2e/ | I | C | C | I | I | R / A
Definition of Done & Sprint Release Sign-Off | A | A | C | I | I | C